Request for Proposal

Appointment of Event Management Agency

For “Yashobhoomi Roadshow in Korea”

1. Background

KINEXIN operates Yashobhoomi in New Delhi. To promote the venue and strengthen Korea–India MICE cooperation, KINEXIN will organize a roadshow event in Korea.

2. Objective of Assignment

To appoint a qualified event management agency to plan, coordinate, and execute the “Yashobhoomi Roadshow in Korea” in a professional and timely manner.

The agency shall ensure seamless event execution including technical setup, guest management, catering coordination, and presentation support.

3. Event Details

- Date: 25 March 2026

- Venue: Grand Ballroom, KINTEX, South Korea

- Participants: Approx. 200 attendees

[Venue Rental Requirement] For smooth stage installation and dismantling, the Grand Ballroom at KINTEX must be rented for five (5) days, tentatively: - 22 & 23 March 2026 – Setup - 24 March 2026 – Technical rehearsal & staging - 25 March 2026 – Event Day - 26 March 2026 – Dismantling The agency shall coordinate all logistics and scheduling with KINTEX.

4. Scope of Work

4.1 Pre-Event Planning

The selected agency shall provide:

- Comprehensive event execution plan and timeline

- Venue coordination with KINTEX

- Stage design and layout plan

- Technical planning (AV, LED screen, AI subtitle system)

- Catering coordination

- Speaker & program coordination

- Invitation design and RSVP management (250–300 invitees)

4.2 SNS Influencer Engagement

The agency shall:

- Coordinate invitation and logistics of one (1) India-based SNS influencer

- Arrange stage setup and presentation support for influencer session

- Manage hospitality, transport coordination, and technical presentation requirements

The influencer shall deliver a “Korea–India Talk” presentation during the main session.

4.3 Catering Requirement

A buffet-style luncheon shall be provided for approximately 200 attendees.

The catering standard shall be equivalent to KRW 100,000 per person, representing a premium corporate buffet level suitable for high-level industry participants.

The agency shall:

- Coordinate menu planning

- Ensure dietary diversity

- Manage serving staff and service quality

4.4 Event Production

The agency shall provide:

- Stage construction and decoration

- Backdrop and branding production

- LED screen and AV equipment

- AI-based Korean–English subtitle support

- On-site registration desk

- Guest protocol support

- Photography and video recording

4.5 Post-Event Deliverables

Within fourteen (14) days after the event:

- Event completion report

- Attendance report

- Media coverage summary (if any)

- Photo and video archive

5. Estimated Budget

The estimated budget for this assignment is:

- INR 9,800,000 (excluding GST)

This amount shall be considered the ceiling budget.

Proposals significantly exceeding this amount may not be considered.

6. Qualification Requirements

- Experience in MICE-related events preferred

- Proven capacity to manage 200+ pax events

- Financial stability

7. Proposal Submission Requirements

Agencies shall submit:

- Qualification supporting documentation

- Financial Proposal (separate sealed envelope)

- Company profile

8. Evaluation Criteria

| Criteria | Weight |
| --- | --- |
| Financial Proposal | 100% |

The lowest responsive bid within the estimated budget shall be considered for award.

9. Proposal Submission Procedure

Interested bidders shall submit their proposals as follows:

- Submission Deadline : at 18:00 6th of March

- Submission Method : Email Submission to: accounting@kinexin.com

10. Contract Type

Lump-sum contract.